## Sheet1
TEAM LEAD | TASKS | SUB-TASKS | TEAM MEMBERS | START DATE | END DATE | GITHUB LINK OF TASKS | REPORT LINK | REMARKS | DEPLOYMENT LINK
Chandra chud singh chundawat | Task 1 - EDA |  | Nanda Gopal | 2021-06-15 | 2021-06-22 | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction/blob/main/Readme.md | It was a very fruitful Internship with Technocolabs Softwares. I had faced many challenges in this duration of my internship, and also received a lot of help and guidance from both our mentor Mr. Sampath Sundaram and also from my teammates. Our project coordinator Mr.Yasin Shah has also been nice and helpful to us and provided us with proper guidance and some career advice. Overall its been a good experience. | https://share.streamlit.io/chandrachudsingh/stock-price-prediction-streamlit-teama/main/app.py
|  |  | Rahul Amarwal | 2021-06-15 | 2021-06-22
|  |  | Sandeep Mannam | 2021-06-15 | 2021-06-22
|  |  | Sunil | 2021-06-15 | 2021-06-22
|  |  | Sital | 2021-06-15 | 2021-06-22
|  |  | Lavanya | 2021-06-15 | 2021-06-22
|  |  | Meghana | 2021-06-15 | 2021-06-22
|  |  | Namrata Sai | 2021-06-15 | 2021-06-22
|  |  | Chandra Chud Singh | 2021-06-15 | 2021-06-22
| Task 2 - Dataset Combining |  |  |  |  | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction/tree/main/Dataset_Combining
|  |  | Namrata Sai | 2021-06-24 | 2021-06-24
|  |  | Sandeep Mannam | 2021-06-24 | 2021-06-24
| Task 3 - Modelling | Linear Regression | Sital Agarwal | 2021-06-25 | 2021-06-30 | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction/blob/main/Linear%20Regression/Linear_regression(2).ipynb
|  |  | Chandra Chud Singh | 2021-06-25 | 2021-06-30
|  |  |  | 2021-06-25 | 2021-06-25
|  | Naïve Bayes | Chandra Chud Singh | 2021-06-25 | 2021-06-30 | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction/tree/main/Naive%20Bayes%20Models%20with%20Hyperparameters%20tuned
|  |  | Namrata Sai | 2021-06-25 | 2021-06-30
|  |  | Meghana | 2021-06-25 | 2021-06-30 |  |  | The Project of Stock Price Prediction of a company was a quite large and nice project. With Technocolabs we explore the project in as wide range as possible and worked on various aspects of it. It's been a great opportunity for me to work on this project. Our mentor Mr. Sampath Sundaram and Project coordinator Mr. Yasin Shah were both too helpful, polite and a good guide to us.
|  | Neural Networks | Nanda Gopal | 2021-06-25 | 2021-06-30 | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction/tree/main/LSTM%20using%2020%20days%20Data
|  |  | Chandra Chud Singh | 2021-06-25 | 2021-06-30
|  |  | Lavanya | 2021-06-25 | 2021-06-30
| Task 4 - Hyperparamter Tuning of Models |  | Sunil | 2021-07-01 | 2021-07-04 | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction
|  |  | Sandeep Mannam | 2021-07-01 | 2021-07-04
|  |  | Chandra Chud Singh | 2021-07-01 | 2021-07-04
|  |  | Rahul Amarwal | 2021-07-01 | 2021-07-04
|  |  | Sital | 2021-07-01 | 2021-07-04
| Task 5 - Model Deployment |  | Chandra Chud Singh | 2021-07-05 | 2021-07-15 | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction/tree/main/LSTM_Streamlit_Deploy_Team%20A
|  |  | Nanda Gopal | 2021-07-05 | 2021-07-15
|  |  | Namrata Sai | 2021-07-05 | 2021-07-15
| Github Handling and Documentation |  |  |  |  | https://github.com/Technocolabs-Group-A/Stock--Price-Prediction
|  |  | Rahul Amarwal | 2021-06-25 | 2021-07-15
|  |  | Sunil | 2021-06-10 | 2021-06-25 | https://github.com/Technocolabs100/Predicting-Stock-Price-Changes-Using-Past-Prices-and-News-Articles-ML1